## Sheet1
Item | Time Needed | Deadline | Feb Wk3 | Feb Wk4 | Mar Wk1 | Mar Wk2 | Mar Wk3 | Mar Wk4 | Apr Wk1 | Apr Wk2 | Apr Wk3 | Apr Wk4 | May Wk1 | May Wk2 | May Wk3 | May Wk4 | Jun Wk1 | Jun Wk2 | Jun Wk 3 | Jun Wk4 | July Wk1 | July Wk2 | July Wk3 | July Wk4
Identify any changes to sims |  | 2021-02-19 | bar: Feb Wk3
Convert and add code to blank doc for pipeline | 1 full day | 2021-02-22 | bar: Feb Wk3
writing goal write intro para 1-3 | 1 full day | 2021-02-28 | bar: Feb Wk4
Analyze control sims | 1 week | 2021-02-26 | bar: Feb Wk4
Run assessment of adaptive inversions on one sim using VA metric and FST outlier? | 2 days | 2021-03-10 | bar: Feb Wk3 to Feb Wk4
writing goal intro para 4-6 | 1 full day | 2021-03-15 | bar: Feb Wk4 to Mar Wk1
finalize most methods | 2 days | 2021-03-10 | bar: Mar Wk2
Determine adaptive inversion criteria | 2-3 days | 2021-03-12 | bar: Mar Wk2
Write up analysis methods | 4-5 hours | 2021-03-16 | bar: Mar Wk3
Rerun sims | 4 days | 2021-04-01 | bar: Mar Wk4 to Apr Wk1
Full Methods Draft | 2 weeks | 2021-03-17 | bar: Mar Wk2 to Mar Wk3
Full Intro 2nd Draft | 2 weeks | 2021-03-26 | bar: Mar Wk3 to Mar Wk4
Run any extra sims | 3 days | 2021-04-07 | bar: Apr Wk2
Analyze full set | 3 weeks | 2021-04-23 | bar: Apr Wk1 to Apr Wk3
Add Figures to Latex documents | 3 days | 2021-04-27 | bar: Apr Wk4
Full Draft Results | 2 weeks | 2021-05-10 | bar: Apr Wk4 to May Wk1
Full Draft Discussion | 2-3 weeks | 2021-05-24 | bar: May Wk1 to May Wk3
Get Full Draft to Collaborators | 1 week | 2021-05-24 | bar: May Wk4
Final Draft of Methods | 1 week | 2021-06-04 | bar: Jun Wk1
Final Draft of Intro | 1 week | 2021-06-11 | bar: Jun Wk2
Add Supplemental data to Latex | 4-5 hours | 2021-06-14 | bar: Jun Wk2
Final Draft of Results | 1 week | 2021-06-25 | [16 empty] | x
Final Draft of Discussion | 1 week | 2021-07-02 | [17 empty] | x | x
Final Draft to collaborators | 1 week | 2021-07-07 | [19 empty] | x
Double check formating | 1 full day | 2021-07-07 | [19 empty] | x
Edit Refs | 4-5 hours | 2021-07-09 | [19 empty] | x
Project Deadline | submit paper | 2021-07-12 | [20 empty] | x